## Sheet1
Problem Area | Description | Mitigation Strategies | Likelihood (H/M/L) | Impact (H/M/L) | Owner
Availability of radiometers | A radiometer may fail onboard a ship for any number of reasons | Ensure a spare radiometer is available to install next time the ship is in its home port. Ensure spare parts are available to quickly repair and test the failed unit. Collect ancilliary data to analyse and rectify problems quickly. | L | H | Operator
Availability of ships | Ship owner may decide to no longer support the radiometer or the ship may be decommissioned or a pandemic can cause rulings to temporarily halt ship deployments. | Negotiate an alternative ship for the radiometer. In the case of Covid-19 restrictions, keep in contact with ship operator for latest rules. | M | H | Operator
Availability of SLSTR data | Data may not be available | If temporary, wait for data to become available before processing for match-ups. If permanent, switch to processing alternative satellite data. | M | L | Operator
Availability of key personnel | Key personnel may not be available at certain times due to sickness or holiday. | Several team members share relevant knowledge so if one person is away another can temporarily do some work and/or answer questions on their behalf. | M | L | PM
Loss of ship to shore communication | IRDIUM/satellite link is lost and access to instrument during deployment is lost | Plan for extra maintenance trip, to get data and check on the instrument performance. | L | L | Operator
Loss of key staff | Key staff member may leave job or be made redundant | Use procedures and documentation to train new staff member. | L | H | Operator
Loss of key facilities | Laboratory space dedicated to the project becomes unavailable. | Move to another laboratory space in the same facility. | L | M | Operator
Loss of computing facilitates | Key processing software/processing computers becomes unavailable. | Make regular back-ups, ensure hardware is well maintained, transfer to new hardware. | L | M | Operator
Loss of power on ship | The ship's power supply to the instrument may be cut off e.g. due to ship maintenance activities, resulting in loss of data. | Provide a UPS to ensure powere is maintained for at least 30 minutes in the even of a temporary loss of ship's power. | M | M | Operator
Failure of weather door on the instrument | The weather door could be stuck either permanently open or permanetly closed. If open, rain or salt water could enter the optics and cause mirror degradation. If closed, data will be lost. | Fix weather door on next visit to port. Examine and fix optics, if required. Examine the data and exclude any that are suspect. | M | M | Operator
COVID-19 | The Covid-19 disease caused by SARS CoV-2 (commonly known as the Coronavirus) has caused an increase in flu-like illnesses and unprecedented actions to be taken by governments and companies around the world to reduce the pandemic. At time of writing, this includes: working-from-home, restricting national and international travel, banning gatherings of 3 or more people (UK). | Working from home reduces the chances of colleagues becoming ill, so work that is feasible to do at home can continue. This can include: document updates, papers, uploading and analysis of SST data already obtained, planning for future deployments, workshops, conferences and next generation radiometers. Operators will keep in contact with their respective ships of opportunity to keep up-to-date with the latest deployment schedules. | H | H | All
BREXIT | The UK is no longer in the EU | Operators of the instruments are aware of the procedures for transporting equipment over the world and will use this experience to continue transporting equipment throughout Europe. Operators will keep up-to-date on the latest rules and regulations. | H | M | All